# Work plan
## Deadlines
- 2017-02-27 Choose a project proposal and send your choice via email to epsatisep@gmail.com
- 2017-03-06 Define the Tasks (what must be done - all members must participate in all tasks), subtask allocation (who does what) and Gantt chart (when) of the project and insert them on the wiki (planning)
- 2017-03-13 Upload the “black box” System Diagrams & Structural Drafts to the wiki
- 2017-03-27 Upload the detailed System Schematics & Structural Drawings to the wiki and finish the cardboard scale model of the structure
- 2017-04-03 Upload the List of Materials (what & quantity) to the wiki
- 2017-04-09 Upload the Interim Report and Presentation to the wiki. The report must contain the Introduction, including the tasks, team members allocation and Gantt chart, State of the Art, Marketing Plan, Project Management, Eco-eficiency Measures for Sustainability, Ethical and Deontological Concerns, Proposed Solution and Bibliography chapters
- 2017-04-24 Complete the List of Materials (local providers & price - including VAT and transportation) to the wiki
- 2017-04-20 Interim Presentation, Discussion and Peer, Teacher and Supervisor Feedbacks
- 2017-05-02 Upload refined Interim Report (based on Teacher & Supervisor Feedbacks)
- 2017-06-05 Upload the Functional Tests' Results to the wiki
- 2017-06-18 Upload the Final Report, Presentation, Video, Paper, Poster and Manual
- 2017-06-22 Final Presentation, Individual Discussion and Assessment
- 2017-06-26:
  - Update the wiki with all correction suggestions
  - Hand in to the EPS coordinator a CD with the corrected deliverables (source + PDF) together with all code and drawings produced
  - Hand in one printed exemplar of the corrected report to the EPS coordinator
- 2017-06-29:
  - Hand in the prototype and user manual to the client
  - Receive the EPS@ISEP certificate
## Tasks
Phase	Task	Responsible	Involved
Initial planning	Purpose definition	All	All
	Task allocation	Margot	All
	Gantt chart	José	All
	Technical research	Jan	All
	Market Research	Margot, Anna	All
	Initial budget planning	Raymond	All
	Purpose definition	All	All
Specific Planning	System diagram	Jan	All
	Structural draft	José	All
	Design	Jan	All
	Materials research and budget replanning	Raymond	All
	Complete list of materials	Margot	All
Interim	Project management	Anna	All
	Eco- efficience measures for sustainability	José	All
	Ethical and deontological concerns	Raymond	All
	Upload interim report and presentation	Anna	All
	Interim presentation	Margot	All
	Upload refined interim report	Anna	All
Construction	Construction Hardware	José and Raymond	All
	Construction Software	Jan	All
Testing	Product testing	All	All
	Corrections	Jan, José and Raymond	All
Final	Final report and presentation upload	Margot	All
	Movie	Jan	All
	Demonstration	Anna	All
	Poster	Margot	All
	Manual	Anna	All
	Leaflet	Margot	All
	Final presentation	Anna	All
	Finish wiki	Margot	All
	Corrected printed report	Anna	All

## Gantt Chart